## DIN Framework Instructions
Decide / Input / Notify (DIN) Framework
This framework was shared Google's PMM Lead, YouTube Shorts, Youtube, Pratik Gadamasetti
Please Make a Copy
Overview: For any project or product launch that involves multiple cross functional (XFN) stakeholders and leadership input, a clear DIN framework can help you organize and streamline all the stakeholders you're working with, what their role is, and ultimately how decisions will be made. Note: This is a lightweight template that is meant to be tailored and expanded upon. Every project/launch is unique so definitely make it your own! Also, the management and ownership of this process may also look different from company to company.
Step 1: DIN Stakeholder List
Establish a DIN Stakeholder List and make sure you reach alignment with your respective XFN leaders before moving forward. This will look different from project to project but a critical step is to always make sure XFN leaders are aligned before moving to step 2.
Step 2: DIN Workback Schedule
Aligned to your overall GTM or launch timeline, make sure you bake in ample time for all steps needed to reach a final decision or set of decisions on a respective project. For example, if you know the head of product is the ultimate decision maker on a product demo, it's important to layout the critical path of who you'll need input from, and who you'll need to notify before reaching a final decision. This will likely involve multiple INPUT and NOTIFY meetings with Eng, Design, and PMs for example.
Step 3: DIN Weekly Forum(s) Tracker
As projects and product launches get more complex, it's critical that you have a week by week view of all the forums, workstreams and decisions made to stay organized and so that you can always point to a source of truth and paper trail for any interested stakeholder.

## DIN Stakeholder List
DIN Stakeholder List
This framework was shared Google's PMM Lead, YouTube Shorts, Youtube, Pratik Gadamasetti
Please Make a Copy
This is a lightweight template that is meant to be tailored and expanded upon. Every project/launch is unique so definitely make it your own! Also, the management and ownership of this process may also look different from company to company.
DIN Stakeholder List
Establish a DIN Stakeholder List and make sure you reach alignment with your respective XFN leaders before moving forward. This will look different from project to project but a critical step is to always make sure XFN leaders are aligned before moving to step 2.
Marketing Stakeholders
Workstream/Deliverable | D(ecide) | I(nput) | N(otify)
Ex: Target Audience Strategy | Insert Name, Title
Sales/Biz Stakeholders
Workstream/Deliverable | D(ecide) | I(nput) | N(otify)
Ex: Sales Pitch Deck | Insert Name, Title
Product/Tech Stakeholders
Workstream/Deliverable | D(ecide) | I(nput) | N(otify)
Ex: Product Demo | Insert Name, Title
Other Stakeholders
Workstream/Deliverable | D(ecide) | I(nput) | N(otify)
Ex: Press Q&A | Insert Name, Title

## DIN Workback Schedule
DIN Workback Schedule
This framework was shared Google's PMM Lead, YouTube Shorts, Youtube, Pratik Gadamasetti
Please Make a Copy
This is a lightweight template that is meant to be tailored and expanded upon. Every project/launch is unique so definitely make it your own! Also, the management and ownership of this process may also look different from company to company.
Workback Schedule
Aligned to your overall GTM or launch timeline, make sure you bake in ample time for all steps needed to reach a final decision or set of decisions on a respective project. For example, if you know the head of product is the ultimate decision maker on a product demo, it's important to layout the critical path of who you'll need input from, and who you'll need to notify before reaching a final decision. This will likely involve multiple INPUT and NOTIFY meetings with Eng, Design, and PMs for example.
Workstream | Review Forum |  |  | Scheduled Date | Meeting Confirmed? | Status | Decide | Input | Notify
Product Demo | XFN Working Group Bi-weekly |  |  | 2024-04-02 | No | Completed |  | X
Product Demo | UX Design Review |  |  | 2024-04-09 | No | Completed |  | X
Product Demo | Tech Leads XFN Review |  |  | 2024-04-23 | No | In progress |  | X
Product Demo | XFN Leads Review |  |  | 2024-04-25 | No | Not started |  | X
Product Demo | Events team walkthrough |  |  | 2024-04-26 | No | Not started |  |  | X
Product Demo | Head of Product Review |  |  | 2024-04-30 | No | Not started | X
DIN Weekly Forum Tracker
As projects and product launches get more complex, it's critical that you have a week by week view of all the forums, workstreams and decisions made to stay organized and so that you can always point to a source of truth and paper trail for any interested stakeholder.
Week Task List
Presenter (name) | Subteam | Topic | Goal (D/I/N) | Goals (Detailed) |  | Invitees to add | Scheduled Date/Time | Pre Read / Review Materials / Notes
MARCH 18-22
D
I
N
MARCH 25-29
D
I
N
APRIL 1-5
D
I
N

## DIN Weekly Forum(s) Tracker
DIN Weekly Forum(s) Tracker
This framework was shared Google's PMM Lead, YouTube Shorts, Youtube, Pratik Gadamasetti
Please Make a Copy
This is a lightweight template that is meant to be tailored and expanded upon. Every project/launch is unique so definitely make it your own! Also, the management and ownership of this process may also look different from company to company.
DIN Weekly Forum Tracker
As projects and product launches get more complex, it's critical that you have a week by week view of all the forums, workstreams and decisions made to stay organized and so that you can always point to a source of truth and paper trail for any interested stakeholder.
Week Task List
Presenter (name) | Subteam | Topic | Goal (D/I/N) | Goals (Detailed) | Invitees to add | Scheduled Date/Time | Pre Read / Review Materials / Notes
MARCH 18-22
D
I
N
MARCH 25-29
D
I
N
APRIL 1-5
D
I
N