## Instructions
GTM Launch Execution Plan
This framework was shared by SurveyMonkey's Senior Director, Head of Product & Solutions Marketing, Morgan Lehman
Please Make a Copy
Purpose of this document: align cross-functional teams working on GTM launches around the full set of activities to support the launch; serve as the source of truth for project status Document owner: The PMM driving the launch will be the owner, but once the launch is kicked off with product, sales, marketing, etc partners, others will be able to contribute & update the doc where needed. Instructions: 1. PMM will align with stakeholders and decide whether the launch is: a) Tier 1 or Tier 2 market launch b) High, medium, or low customer impact launch 2. PMM will remove any unnecessary tabs in this execution plan All launches will leverage: - The product readiness tab - Up to ONE of the market launch tabs (Tier 1 or Tier 2; or none if not applicable) - Up to ONE of the customer impact tabs (High, Med, or Low; or none if not applicable) - The post-launch measurement tab 3. PMM will review the acitivies in each tab, adding or removing where appropriate (e.g. if you won't be running a beta program, remove that section). If you'd like, you can combine everything remaining into a single tab for one full view of your execution plan. 4. PMM will adjust the dates at the top of the gantt chart to account for your project timeline, making note of scheduled holidays or industry/customer events. 5. PMM will use this as a guide when hosting the launch kick off, start assigning drivers, and leverage this doc to keep teams accountable to agreed upon timelines. 6. Collaborators will be given access to this doc to edit their sections & keep project status up to date.

## HIGH Customer Impact
GTM Launch Execution Plan
This framework was shared by SurveyMonkey's Senior Director, Head of Product & Solutions Marketing, Morgan Lehman
Please Make a Copy
HIGH Customer Impact Launch Activities |  |  |  | Quarter | Q3 | [65 empty] | Q4
|  |  |  | Month | July | [21 empty] | August | [21 empty] | September | [21 empty] | October | [20 empty] | November | [21 empty] | December
|  |  |  | Date | 2022-07-01 | 2022-07-02 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31
|  |  |  | Day | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
|  |  |  | External dates (holidays, etc) | [52 empty] | Cust. Event
Initiative |  | Driver Name | Due date | Day: Project link
Customer Comms
FALSE | Customer segmentation
TRUE | Pull any necessary data/lists | bar: Th to Th
FALSE | Define customer launch segments | bar: Th to Th
FALSE | Document customer comms strategy
FALSE | Channels (email, in-product, 1:1, etc)
FALSE | Comms schedule/phases timing
FALSE | Messaging framework
FALSE | Customer-specific messaging (w/ Customer Mktg)
FALSE | Legal approval of messaging
FALSE | Internal readiness
TRUE | Product/Initiative FAQ
TRUE | Sales & Success training
FALSE | CustOps training
FALSE | Marketing/Comms training
FALSE | In-Product Comms
FALSE | In-product targeting
FALSE | In-product UX copy/design
FALSE | In-product Banner
FALSE | In-product entry points
FALSE | Update transactional emails
FALSE | Error message (for outage)
FALSE | Help Center customer facing FAQs
FALSE | Marketing Comms
FALSE | Upload/create customer send lists
FALSE | Email copy/creative
FALSE | Email L10N (loop in early!)
FALSE | Marketing ad-hoc email(s)
FALSE | Marketing newsletter (SFMC)
FALSE | Marketing newsletter (Hubspot)
FALSE | Website banners
FALSE | Social media posts
FALSE | Sales/Success Comms
FALSE | 1:1 Customer email templates
FALSE | Customer-facing FAQ
FALSE | CustOps Comms
TRUE | Publish page in CustOps wiki
FALSE | CustOps email signature
FALSE | CustOps customer case category
FALSE | CustOps case QTs (incl L10N)
FALSE | Social Care team preparedness
FALSE | Day-Of Activation
FALSE | Cut-over plan (e.g. re-directs)
FALSE | Slack channel announcements
FALSE | Customer-facing team reminders
FALSE | Monitor customer case volume
Customer Onboarding & Expansion
FALSE | Customer onboarding
FALSE | New customer onboarding strategy
FALSE | Onboarding email sequence
FALSE | Getting started guide
FALSE | Customer-facing how-to videos
FALSE | Customer training / best practices
FALSE | Customer Engagement
FALSE | QBR template updates
FALSE | Customer touchpoints (email, etc)
FALSE | Customer Expansion
FALSE | Expansion playbook updates
FALSE | Renewal process & playbook
FALSE | Gainsight CTAs

## Product Readiness
GTM Launch Execution Plan
This framework was shared by SurveyMonkey's Senior Director, Head of Product & Solutions Marketing, Morgan Lehman
Please Make a Copy
Product Readiness Activities |  |  |  | Quarter | Q3 | [65 empty] | Q4
|  |  |  | Month | July | [21 empty] | August | [21 empty] | September | [21 empty] | October | [20 empty] | November | [21 empty] | December
|  |  |  | Date | 2022-07-01 | 2022-07-02 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31
|  |  |  | Day | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
|  |  |  | External dates (holidays, etc) | [52 empty] | Cust. Event
Initiative |  | Driver Name | Due date | Day: Project link
Product Readiness
FALSE | Product release | PM | bar: Th to Fr
TRUE | Feature X release | PM | bar: Th to Th
TRUE | Feature Y release | PM | bar: Mo to Fr
TRUE | Eng bug bash | Eng
FALSE | Feature flag for roll-back or grandfathering | Eng | bar: Mo to Th
TRUE | Transactional emails | Eng | bar: Mo to Th
FALSE | Product discovery | PM | bar: Mo to Th
FALSE | In-product entry points | PM | bar: Mo to Th
FALSE | In-product banners | PM | bar: Mo to Th
FALSE | Pricing strategy | Pricing | bar: Mo to Th
FALSE | Customer research | Pricing
FALSE | Pricing model / plan tier | Pricing
FALSE | Deliver pricing calculator | Pricing
FALSE | Align on sales discount threshold | Pricing
FALSE | Beta/EAP program | PM
TRUE | Customer recruitment | CSM, PM | bar: Th to Th
FALSE | Customer onboarding | CSM
FALSE | Internal CSM beta | PM/CSM
FALSE | Feedback consolidation | PM
FALSE | Launch partner recruitment | CSM/Cust Mktg/PR
FALSE | Product naming | PMM
TRUE | Shortlist approval (brand) | PMM
TRUE | Shortlist legal approval | PMM
FALSE | Name testing (quant/qual) | PMM
FALSE | Final name decision | PMM
FALSE | Product Messaging | PMM
TRUE | Competitive research | PMM
FALSE | Define ideal customer profile | PMM
FALSE | Deliver messaging framework | PMM
FALSE | Help center article | PM
FALSE | Internal product demo | PM
FALSE | Demo outline/script | PM/PMM
FALSE | Recorded demo video | PM

## TIER 1 Market Launch
GTM Launch Execution Plan
This framework was shared by SurveyMonkey's Senior Director, Head of Product & Solutions Marketing, Morgan Lehman
Please Make a Copy
Tier 1 Market Launch Activities |  |  |  | Quarter | Q3 | [65 empty] | Q4
|  |  |  | Month | July | [21 empty] | August | [21 empty] | September | [21 empty] | October | [20 empty] | November | [21 empty] | December
|  |  |  | Date | 2022-07-01 | 2022-07-02 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31
|  |  |  | Day | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
|  |  |  | External dates (holidays, etc) | [52 empty] | Cust. Event
Initiative |  | Driver Name | Due date | Day: Project link
FALSE | Document launch timeline & user flow | PMM w/ channel leads
Sales & Success Readiness
FALSE | Sales Strategy | Sales Strategy/Ops
TRUE | Define target account list | Sales Ops | bar: Th to Th
FALSE | Contract readiness | Legal | bar: Th to Th
TRUE | SKU creation (see process) | Sales Ops | bar: Th to Th
FALSE | Sales (AE, BDR, SDR, SE, CSM) Training | PMM, Sales Enablement
TRUE | Product Overview + Cheat Sheet | PMM
TRUE | Personas, value props, use cases | PMM
FALSE | Update Sales Playbook | PMM/Enablement
FALSE | Competitive battle cards | PMM
FALSE | Discovery | PMM
FALSE | Pitch certification | PMM
FALSE | Pricing / scoping training | Pricing, SE
FALSE | Demo certification | PMM
FALSE | Cross-sell training | PMM/Enablement
FALSE | Launch activation | PMM
FALSE | Post-sales (SE, CSM, CustOps, PS, Delivery) Training | PM, CS Enablement
FALSE | Full product walkthrough | PM
FALSE | Product admin training | PM
FALSE | Customer messaging | PMM
FALSE | SDR / BDR Training | PMM
FALSE | Outbound discovery | PMM
FALSE | BDR launch blitz campaign | DG/Enablement
FALSE | Inbound follow-up | PMM/DG
FALSE | Customer-facing materials | PMM
TRUE | Pitch deck | PMM
TRUE | One-pager | PMM
FALSE | Outreach email templates | PMM
FALSE | Update existing collateral | PMM
FALSE | Update Highspot hub | Enablement
FALSE | Customer stories | Cust Mktg
FALSE | Localization where appropriate (loop in early!) | L10N
Marketing Launch
FALSE | External comms | Comms
FALSE | Comms plan | PR
FALSE | Organic social media posts | Social
FALSE | Analyst outreach/briefing | Analyst Relations
FALSE | Investor outreach/briefing | IR
FALSE | Shareholder letter | IR
FALSE | Content / thought leadership | PMM
FALSE | Blog announcement | PMM
FALSE | Webpage / landing page | PMM
FALSE | Tile in solutions marketplace | PMM
FALSE | SEO content | SEO
FALSE | Website cross-linking & promotion | Web pod
FALSE | Website experimentation | Web pod
FALSE | Sponsored content | Content
FALSE | Ebook/guide | Content
FALSE | Product overview video | PMM
FALSE | Product demo video | PMM
FALSE | Localization where appropriate (loop in early!) | L10N
FALSE | Lead gen programs | DG
FALSE | Define ABM account list | DG
FALSE | Prospect webinar | DG
FALSE | Customer webinar | Cust Mktg
FALSE | Events / round tables | DG
FALSE | Content syndication | DG
FALSE | Email announcements | DG/LCM
FALSE | Email nurtures/newsletters | DG/LCM
FALSE | Paid campaigns | Paid/DG
FALSE | Final launch assets review with Approver | PMM
Internal Launch
FALSE | Launch "Top 5" doc | PMM
FALSE | Product description | PMM
FALSE | Key value props | PMM
FALSE | Outbound message to contacts | PMM
FALSE | Content to share | Content
FALSE | Social media posts to share | Social
FALSE | Internal comms | PMM
FALSE | Create a Internal wiki page | PMM
FALSE | Post to internal slack channels | PMM
FALSE | "Weekly insider" newsletter | Internal Comms
FALSE | Sales enablement newsletter | Enablement
FALSE | CustOps newsletter | PM
FALSE | Internal town hall | Internal Comms
FALSE | Internal lunch & learn | PMM
FALSE | Executive team + pillar leads biweekly launch update emails | PMM/PM/Sales

## TIER 2 Market Launch
GTM Launch Execution Plan
This framework was shared by SurveyMonkey's Senior Director, Head of Product & Solutions Marketing, Morgan Lehman
Please Make a Copy
Tier 2 Market Launch Activities |  |  |  | Quarter | Q3 | [65 empty] | Q4
|  |  |  | Month | July | [21 empty] | August | [21 empty] | September | [21 empty] | October | [20 empty] | November | [21 empty] | December
|  |  |  | Date | 2022-07-01 | 2022-07-02 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31
|  |  |  | Day | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
|  |  |  | External dates (holidays, etc) | [52 empty] | Cust. Event
Initiative |  | Driver Name | Due date | Day: Project link
FALSE | Document launch timeline & user flow | PMM w/ channel leads
Sales & Success Readiness
FALSE | Sales (AE, BDR, SDR, SE, CSM) Training | PMM, Sales Enablement
TRUE | Product Overview + Cheat Sheet | PMM
FALSE | Update Sales Playbook | PMM/Enablement
FALSE | Pricing / scoping training | Pricing, SE
FALSE | Cross-sell training | PMM/Enablement
FALSE | Launch activation | PMM
FALSE | Post-sales (SE, CSM, CustOps, PS, Delivery) Training | PM, CS Enablement
FALSE | Full feature walkthrough | PM
FALSE | Product admin training | PM
FALSE | Customer messaging | PMM
FALSE | Customer-facing materials | PMM
FALSE | Outreach email templates | PMM
FALSE | Update existing collateral | PMM
FALSE | Update Highspot hub | Enablement
FALSE | Customer stories | Cust Mktg
FALSE | Localization where appropriate (loop in early!) | L10N
Marketing Launch
FALSE | External comms | Comms
FALSE | Comms plan | PR
FALSE | Content / thought leadership | PMM
FALSE | Blog announcement | PMM
FALSE | Update webpage / landing page | PMM
FALSE | Update SEO content | SEO
FALSE | Update product demo video | PMM
FALSE | Localization where appropriate (loop in early!) | L10N
FALSE | Lead gen programs | DG
FALSE | Customer webinar | Cust Mktg
FALSE | Email announcements | DG/LCM
FALSE | Email nurtures/newsletters | DG/LCM
FALSE | Final launch assets review with Approver | PMM
Internal Launch
FALSE | Launch "Top 5" doc | PMM
FALSE | Feature description | PMM
FALSE | Key value props | PMM
FALSE | Outbound message to contacts | PMM
FALSE | Content to share | PMM
FALSE | Social media posts to share | Social
FALSE | Internal comms | PMM
FALSE | Create a Internal wiki page | PMM
FALSE | Post to internal slack channels | PMM
FALSE | Sales enablement newsletter | Enablement
FALSE | "Weekly insider" newsletter | Internal Comms

## MED Customer Impact
GTM Launch Execution Plan
This framework was shared by SurveyMonkey's Senior Director, Head of Product & Solutions Marketing, Morgan Lehman
Please Make a Copy
MEDIUM Customer Impact Launch Activities |  |  |  | Quarter | Q3 | [65 empty] | Q4
|  |  |  | Month | July | [21 empty] | August | [21 empty] | September | [21 empty] | October | [20 empty] | November | [21 empty] | December
|  |  |  | Date | 2022-07-01 | 2022-07-02 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31
|  |  |  | Day | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
|  |  |  | External dates (holidays, etc) | [52 empty] | Cust. Event
Initiative |  | Driver Name | Due date | Day: Project link
Customer Comms
FALSE | Customer segmentation
TRUE | Pull any necessary data/lists | bar: Th to Th
FALSE | Define customer launch segments | bar: Th to Th
FALSE | Document customer comms strategy
FALSE | Channels (email, in-product, 1:1, etc)
FALSE | Comms schedule/phases timing
FALSE | Messaging framework
FALSE | Customer-specific messaging (w/ Customer Mktg)
FALSE | Legal approval of messaging
FALSE | Internal readiness
TRUE | Product/Initiative FAQ
TRUE | Sales & Success training
FALSE | Marketing Comms
FALSE | Upload/create customer send lists
FALSE | Email copy/creative
FALSE | Email L10N (loop in early!)
FALSE | Marketing newsletter (SFMC)
FALSE | Marketing newsletter (Hubspot)
FALSE | Sales/Success Comms
FALSE | 1:1 Customer email templates
FALSE | Customer-facing FAQ
FALSE | CustOps Comms
TRUE | Publish page in CustOps wiki
FALSE | CustOps case QTs (incl L10N)
FALSE | Day-Of Activation
FALSE | Slack channel announcements
FALSE | Customer-facing team reminders
Customer Onboarding & Expansion
FALSE | Customer onboarding
FALSE | Update onboarding email sequence
FALSE | Update getting started guide
FALSE | Customer Engagement
FALSE | QBR template updates
FALSE | Customer touchpoints (email, etc)
FALSE | Customer Expansion
FALSE | Expansion playbook updates
FALSE | Gainsight CTAs

## LOW Customer Impact
GTM Launch Execution Plan
This framework was shared by SurveyMonkey's Senior Director, Head of Product & Solutions Marketing, Morgan Lehman
Please Make a Copy
LOW Customer Impact Launch Activities |  |  |  | Quarter | Q3 | [65 empty] | Q4
|  |  |  | Month | July | [21 empty] | August | [21 empty] | September | [21 empty] | October | [20 empty] | November | [21 empty] | December
|  |  |  | Date | 2022-07-01 | 2022-07-02 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31
|  |  |  | Day | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
|  |  |  | External dates (holidays, etc) | [52 empty] | Cust. Event
Initiative |  | Driver Name | Due date | Day: Project link
Customer Comms
FALSE | Internal readiness
TRUE | Product/Initiative FAQ
FALSE | Customer-facing team trainings
FALSE | Internal email/slack FYI
FALSE | CustOps Comms (Reactive)
FALSE | Publish page in CustOps wiki
FALSE | CustOps case QTs (incl L10N)
FALSE | Day-Of Activation
FALSE | Slack channel announcements

## Post-Launch Measurement
GTM Launch Execution Plan
This framework was shared by SurveyMonkey's Senior Director, Head of Product & Solutions Marketing, Morgan Lehman
Please Make a Copy
Post-Launch Measurement Activities |  |  |  | Quarter | Q3 | [65 empty] | Q4
|  |  |  | Month | July | [21 empty] | August | [21 empty] | September | [21 empty] | October | [20 empty] | November | [21 empty] | December
|  |  |  | Date | 2022-07-01 | 2022-07-02 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31
|  |  |  | Day | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr
|  |  |  | External dates (holidays, etc) | [52 empty] | Cust. Event
Initiative |  | Driver Name | Due date | Day: Project link
Post-Launch Measurement
FALSE | Metrics and Dashboards
FALSE | GA reports for web traffic | Web analytics
FALSE | Pipeline campaign dashboard | DG
FALSE | Bookings dashboard | DG / Sales / BI
FALSE | Product usage funnel dashboard | BI
FALSE | Renewal dashboard | CSM
FALSE | Launch post-mortem feedback session | PMM
FALSE | Feedback from the field | PMM
FALSE | Establish Sales feedback loop | PMM
FALSE | Running agenda item on GTM syncs | PMM
FALSE | Establish CS feedback loop | PMM
FALSE | Establish CustOps feedback loop | PM
FALSE | Customer feedback / interviews
FALSE | Win/Loss program | PMM/CI
TRUE | Post-launch performance read-out | PMM + channel owners | ~3-6mo post-launch
FALSE | Product iteration/improvement | PM
FALSE | P0 bug fixes | Eng
FALSE | V1 roadmap | PM
FALSE | Roadmap backlog | PM

## User Flow Inputs (hidden)
Assets | Channels | GOAL
HBR partnered research report | Email | Generate MQLs
Persona LP | Paid (geofence, paid social, SEM, content synd) | Lose to ourselves (de-escalator)
Attention quiz | In Product (overlay)
Attention framework LP (possibly anchor linked from persona LP) | On Site (overlay)
Buzzfeed-style video | SEO
Webinars (3 in total) | Paid social
Email
Social channels
PR (maybe)
Partner channels (maybe)