## CampaignLaunches-RACI
Stakeholder Managment Template
This template accompanies the AMA by Databricks Senior Director of Demand Generation, Kelley Sandoval
Please Make a Copy
R = Responsible - Who is responsible for doing the actual work for the project task. A = Accountable - Who is accountable for the success of the task and is the decision-maker. Typically the campaign manager. (*This should be one person whenever possible so as to avoid confusion and slow decision-making.) C = Consulted - Who needs to be consulted for details and additional info on requirements. Typically the person (or team) to be consulted will be the subject matter expert. I = Informed - Who needs to be kept informed of major updates. Typically senior leadership.
Deliverable | Details/Description |  | Team
|  | Approver | Global Campaigns Manager | Product Marketing Manager | Industry Marketing Manager | Techincal Marketing Manager | AMER Pan-AMER | AMER BU Pod Leads | EMEA Pan-EMEA | APAC Pan-APJ | Global Comms | Analyst Relations | Marketing Ops | Dig Media | Organic Social | Content (Copy) | Creative (Visual Expression of Brand) | Customer Advocacy | Analytics | Web | Enablement | Corporate Events | Exec Events | 3P Events | Foundational Campaigns
Messaging is Defined
Define the message | Write and maintain the messaging brief | PMM Leader | I | R/A | C | C | I | I | C | C | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I
APPROVAL
Planning is Aligned
Step 1 - Objective, Strategy, Targets, Budget | Define and align on campaign objective, strategy, and KPIs based on current performance, company goals, and what the persona best responds to. | CMM Leader | R/A | C | C | I | C | C | C | C | I | I | I | I | I | I | I | I | C | I | I | I | I | I | I
APPROVAL
Content Plan
Host KOC for content brainstorm | Brainstorm on the content / BOM for the campaign |  | R/A | C | C | C | C | C | C | C | I | C | - | C | C | C* | I | C | - | C | C | I | C | I | I
Step 2 - Content | Define the key assets needed to bring the campaign to life. Host a brainstorm and finalize what the BOM will be for the program. This may be constrained by timelines, budgets, or resources. | CMM Leader | R/A | C | C | C | C | C | C | C | I | C | - | C | C | C | I | C | - | C | C | I | C | I | I
APPROVAL
Channels are Set
Step 3 - Channel Mix & Strategy | Determine the final strategy and mix the assets will be served against. This includes plans from our channel partners on how each channel will go to market. | CMM Leader | R/A | I | I | I | C | I | C | C | I | I | I | C | I | I | I | I | I | I | I | I | I | I | I
Host KOC for channel owners | Review persona, messaging, and content / BOM |  | R/A | I | I | I | C | I | C | C | I | I | I | I | I | I | I | I | I | I | I | I | C | I | I
Digital Plan | Digital media plan based on assets coming from the campaign and taking note of required targets for their area of the business. | Digital Leader | C | I | I | I | C | I | C | C | - | - | I | R/A | - | I | I | - | I | I | - | - | - | - | -
Web Plan | Plan of what web updates are needed, journeys/cross-CTAs, SEO, and overall web promotional strategy and taking note of required targets for their area of the business. | Web Leader | C | C | C | I | I | I | C | C | - | - | I | I | I | I | I | I | I | R/A | - | I | - | - | I
Organic Social Plan | Plan of what will be posted on organic social when and where | Brand Leader | C | C | C | I | I | I | C | C | I | - | I | - | R/A | I | I | I | I | I | I | - | - | - | -
Event/Partner Programs in a box Plan | Plan of any boxed materials for field or partner | AMER, EMEA, APJ Leaders | R/A | C | C | C (R/A for any specific technical content needs like demos) | C | C | C | C | - | - | I | I | I | I | I | I | I | I | I | C | C | C | -
Direct Mailer Plan | Plan of any direct mailer efforts | CMM Leader | R/A | C | C | I | C | C | C | C | - | - | I | I | I | I | I | I | I | I | I | I | I | I | -
Email Calendar | Calendar of email promotional sends to this audience | Mops Leader | R/A | C/A | C | I | C | C | C | C | - | - | C | I | I | I | I | I | I | I | I | C | C | I | C
Nurture Plan | Details of any specific nurtures to support this effort | Mops Leader | C | C | C | I | I | I | C | C | - | - | C | I | - | I | I | I | I | I | - | I | I | I | R/A
Localization Plan | Details on what will be localized and leveraged by APJ and EMEA | AMER, EMEA, APJ Leaders | C | C | C | I | I | I | R/A | R/A | - | - | I | I | I | I | I | C | I | I | I | - | - | - | I
Personalization & A/B Test Strategy | Plan of elements we may want to test pesonalizing overlays, A/B testing across web, email, etc |  | R/C | C | C | I | C | I | C | C | - | - | C | C | C | C | C | - | I | C | - | I | I | I | R/A
Enablement Strategy | How we will educate the field on what's new and what's coming |  | R/A | R | R | C (R/A for any specific technical content needs like demos) | C | I | C | C | - | - | I | - | - | - | - | - | - | - | C/R | I | I | I | R
Final Approvals on full campaign plan | Have full plan from messaging, content, to channels approved by leadership. This should include the plan on a page from the full persona pod team. | DG Leaders | R/A | I | I | I | bar: C C I I C C to - C R/A I R/A R
APPROVAL
Campaign Execution
Workbacks and Launch Schedule | Align project schedule and outline key deliverable dates based on SLAs |  | R/A | C | C | C | bar: C C I I C C to - C R/A I R/A R
Creative Brief Creation | Buildout of campaign brief and all elements of the segmentation, messaging, and content needs |  | R/A | R | R | C (R/A for any specific technical content needs like demos) | I | I | I | I | - | - | I | R | I | I | I | - | - | I | - | - | - | - | -
Mops submissions | Submission of brief to Asana to begin work with cross functional teams |  | R/A | - | - | - | bar: C C I I C C to - C R/A I R/A R
Content & Design | Build of content and creative needs for campaign programs |  | R/A | R/C | R/C | R/C | - | - | C | C | - | - | - | - | I | R | R | - | - | C | - | - | - | - | -
Web Build | Build of web needs for campaign programs |  | R/A | - | - | - | - | - | - | - | - | - | C | - | - | I | I | - | - | R | - | - | - | - | -
Audience Governance: Message Approvals | Approves what the audience will receive from a messaging standpoint. |  | C | A | C | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Audience Governance: Database Health Approvals | Approves the email sends based on the type and past performance from other teams. |  | A | C | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | C
MOps Build | MOps buildout of emails and and form sync needed across program |  | R/A | - | - | - | - | - | - | - | - | - | R | - | - | - | - | - | - | C | - | - | - | - | -
Organic Social | Organic social & employee advocacy post creation request - Seperate request system from overall creative brief |  | R/A | R | R | I | I | I | I | I | C | - | - | - | R | I | R | - | - | R | I | - | - | - | -
Blog Development | Build out of blog post content for campaign |  | R/A | R | R | R/C | I | I | I | I | I/C | - | - | - | R | - | - | - | - | R | I | - | - | - | -
Paid Media Execution | Building out the media plan based on the creative brief, assesing the content/creative proposed, aligning with the agency and launching the program |  | A | C | C | I | I | I | C | C | I | - | - | R/A | I | - | - | - | C | - | - | - | - | - | -
Third Party Content Programs | Management of third party content, webinar, or other promotional programs |  | R/A | R/C | R/C | I | I | I | I | I | - | - | I | R/A | - | - | - | - | - | - | I | - | - | - | -
Review Cycles w/ Stakeholders | Managing the review cycles of brief progression - content, creative, and web build approvals |  | R/A | I | I | I | - | - | - | - | - | - | C | C | - | C | C | - | - | C | - | - | - | - | -
Playbook/Event in a Box | Creating an event kit | AMER, EMEA, APJ Leaders | R/A | C | C | C (R/A for any specific technical content needs like demos) | C | C | C | C | - | - | - | - | - | R | R | C/I | - | I | - | C/I | C/I | C/I | -
Training Specific Materials | Creating new L&D T&C Offer | PMM Leads | R/A | A (Training PMM) | C | C | I | I | I | I | - | - | I | I | I | R | R | - | - | R | - | - | - | - | I
Enablement Materials | Build of materials for the field related to the campaign - pitch materials, email templates, social assets, Zoom backgrounds, video explainer, go/sales updates, etc. | PMM Leads | C | R | R | C | R/A | C | R/A | R/A | - | - | - | - | C | C* | C* | - | - | - | R/A | - | - | - | R
SDR/BDR Templates | Templates for outreach and lead follow up for campaign and programs |  | R/A | C | C | C | R | R | R | R | - | - | - | - | - | - | - | - | - | - | R/A | - | - | - | R
Enablement Rollout | Bringing awareness to the field of what's new, what's happening, and how to action on it |  | C | R | R | R | R | R | R | R | - | - | - | - | - | - | - | - | - | - | R/A | - | - | - | R
Tracking & Analysis
Submission of Quarterly SFDC campaigns needed |  |  | R/A | I | I | I | R | R | R | R | I | I | R | I | I | - | - | - | I | I | I | - | - | - | -
Building of SFDC campaigns |  |  | R/A | I | I | I | R | R | R | R | I | I | C | I | I | - | - | - | I | I | I | - | - | - | -
Tracking codes: ITM/UTMs | Build of tracking codes needed across web and external links to properly track campaign success |  | R/A | I | I | I | R | R | R | R | - | - | R | R | R | - | - | - | C | R | - | - | - | - | -
Updating SFDC to reflect campaign spend and response status |  |  | A | - | - | I | R | R | R | R | - | - | - | R | - | - | - | - | - | - | - | - | - | - | -
Dashboard views | Build and maintinence of campaign dashboard views to measure effectiveness across campaign |  | A | I | I | I | I | I | I | I | I | I | R | R | I | - | - | - | R/A | R | I | I | I | I | -
Reporting, Learning & Optimizing
Sales reporting calls |  | AMER, EMEA, APJ Leaders | C | C | C | C | C | R/A | R/A | R/A | C | C | - | - | C | - | - | C | - | - | C | C | C | C | -
Internal reporting calls in marketing | A monthly review on the data thus far and what is working and not working and what we can optimize. Iterate on messaging based on learnings in market |  | R/A | C | C | C | C | C | C | C | - | - | I | R | R | I | I | I | R | R | - | I | I | I | R
Retro | Host retro with core campaign team |  | R | C | C | C | C | C | C | C | C | C | C | C | C | C/I | C | C | C/I | C | C | C | C | C | C
Campaign Calls | Presenting updates and learnings on the bi-weekly Global Campaigns Calls |  | R/A | R/C | R/C | R/C | C | I | I | I | - | - | - | C | - | - | - | - | C | C | - | I | I | I | R
QBRs | Putting together a review of the Quarter performance | DG Leaders | R/A | C | C | C | C | C | C | C | - | - | R | R | - | - | - | - | R | R | - | - | - | - | R

## Approvaltracking
Stakeholder Managment Template
This template accompanies the AMA by Databricks Senior Director of Demand Generation, Kelley Sandoval
Please Make a Copy
Use this template at the end of each slide deck to track approvals
Stakeholder |  |  | Commitment
Name/Role | Decision Maker | Approved |  | Date | Comment
Final Decision